## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11942 | New | Water Supply Scheme for Spring Sidi Tea Garden village Piped Water Supply Scheme In Kurseong Under Darjeeling District. |  |  | ORD/000320/2022-2023 | 2644/NKWSMD | 24/02/2023 | 23/08/2023 | HIMALAYAN CONSTRUCTION | 217.45 | 12.5 | 5.75 | 50
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11942 | New | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 700/NKWSMD | 22/03/2024 |  | Resource Division | 1.52 | 0 | 0 | 0
Total | [13 empty] | 218.97 | 12.5 | 5.71