## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11943 | New | Augmentation of Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme, Block: Kurseong, District: Darjeeling. |  |  | ORD/000014/2024-2025 | 979/NKWSMD | 18/06/2024 | 17/08/2024 | SUNRISE ENTERPRISES | 24.35 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11943 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Kurseong Division, P.H.E.D., GTA. | Assistant Engineer II |  | ORD/000262/2023-2024 | 160/AE-II/NKWSMD | 10/01/2024 | 25/01/2024 | MS JAGANNATH PRASAD | 12.44 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11943 | New | Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme in Kurseong Under Darjeeling District. |  |  | ORD/000286/2022-2023 | 2081/NKWSMD | 10/01/2023 | 09/07/2023 | SUNRISE ENTERPRISES | 185.86 | 134.09 | 72.14 | 100
Total | [13 empty] | 222.66 | 134.09 | 60.22