## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12736 | New | Water Supply Scheme for MIM Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  |  | ORD/000255/2022-2023 | 1618/NKWSMD | 03/11/2022 | 02/05/2023 | GARGO TRADERS | 1270.33 | 1049.72 | 82.63 | 95
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12736 | New | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 1896/NKWSMD | 15/12/2022 |  | Resource Division | 6.1 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12736 | New | Material Requisition To Resource Division |  |  | RTOR000178/2022-2023 | 2612/NKWSMD | 17/02/2023 |  | Resource Division | 6.1 | 0 | 0 | 0
Total | [13 empty] | 1282.53 | 1049.72 | 81.85