## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | MAJUA PIPED WATER SUPPLY SCHEME. | SM/15874 | New | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000025/2023-2024 | 124/NKWSMD | 28/04/2023 | 25/10/2023 | DENDUP BHUTIA AND COMPANY | 255.41 | 36.25 | 14.19 | 50
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | MAJUA PIPED WATER SUPPLY SCHEME. | SM/15874 | New | Strengthening of mainline of water supply scheme at Majua (Singhbumdera) under Darjeeling Division, PHED-GTA. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000118/2023-2024 | 861/NKWSMD | 31/07/2023 | 29/09/2023 | RISHI KESH THAKURI | 28.53 | 27.5 | 96.38 | 100
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | MAJUA PIPED WATER SUPPLY SCHEME. | SM/15874 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 243/NKWSMD | 12/05/2023 |  | Resource Division | 1.08 | 0 | 0 | 0
Total | [13 empty] | 285.02 | 63.75 | 22.37