## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Selim Hill Tea Garden | SM/15652 | New | SURFACE WATER BASED SELIM HILL TEA GARDEN TO ACCOMODATE FHTC IN KURSEONG BLOCK |  |  | ORD/000341/2022-2023 | 2756/NKWSMD | 09/03/2023 | 08/03/2024 | SHAKTI CONSTRUCTION | 910.25 | 192.42 | 21.14 | 50
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Selim Hill Tea Garden | SM/15652 | New | Material Requisition To Resource Division |  |  | RTOR000259/2022-2023 | 2771/NKWSMD | 10/03/2023 |  | Resource Division | 2.37 | 0 | 0 | 0
Total | [13 empty] | 912.61 | 192.42 | 21.08