## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/06844 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NGAISUREE T.G. Area piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte.(Phase-II). | Assistant Engineer | Junior Engineer | ORD/000085/2020-2021 | 1273/JD | 18/11/2020 | 16/02/2021 | SADHAN KARMAKAR | 43.64 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/06844 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of GORALBARI (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-A) |  | Junior Engineer | ORD/000223/2020-2021 | 94/JD | 14/01/2021 | 28/02/2021 | SAPTASWA SARKAR | 28 | 12.25 | 43.74 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/06844 | Retrofitting | providing fhtc for maynatali pwss |  |  | VCH/000362/2021-2022 | 357/21-22 | 16/09/2021 |  | SANJIT SAHA | 19.92 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/06844 | Retrofitting | LDS FOR D-SHALBARI PWSS |  |  | VCH/000509/2021-2022 | 336/21-22 | 04/10/2021 |  | ROY & SARKAR CONSTRUCTION | 5.85 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/06844 | Retrofitting | RETROFITTING WORK AT BOALMARI PWSS |  |  | VCH/001782/2020-2021 | 1564 | 19/03/2021 |  | UMWELT ENGINEER PRIVATE LIMITED | 4.34 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/06844 | Retrofitting | RETROFITTING WORK RELATED FHTC FOR BOALMARI PWSS |  |  | VCH/001786/2020-2021 | 1563 | 19/03/2021 |  | UMWELT ENGINEER PRIVATE LIMITED | 4.21 | 0 | 0 | 0
Total | [13 empty] | 105.95 | 12.25 | 11.56