## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | SM/06957 | Retrofitting | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JALDHARA /JAL SAPNA UNDER THE COMMAND AREA OF HILLA T.G. AREA PIPED WATER SUPPLY SCHEME AT NAGRAKATA BLOCK UNDER JALPAIGURI DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000326/2021-2022 | 149/JD | 19/01/2022 | 18/02/2022 | SCEC BOENTER KDAS JOINT VENTURE | 26.95 | 0 | 0 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | SM/06957 | Retrofitting | hire charge |  |  | VCH/000534/2022-2023 | BP-2021-22-208 | 29/09/2022 |  | RAKESH SARKAR | 0.34 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | SM/06957 | Retrofitting | car hire charge |  |  | VCH/000535/2022-2023 | BP-2021-22-207 | 29/09/2022 |  | APIKUL ALI | 0.34 | 0 | 0 | 0
Total | [13 empty] | 27.63 | 0 | 0