## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Ambari Falakata piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000025/2021-2022 | 745/JD | 13/05/2021 | 02/06/2021 | GOURAB GUHA ROY | 14.13 | 14.12 | 99.99 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Ambari Falakata piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000043/2021-2022 | 1069/JD | 02/07/2021 | 23/07/2021 | PRAHLAD PRASAD SAHA | 4.83 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000102/2021-2022 | 1340 /JD | 23/08/2021 | 22/09/2021 | MONTOSH GHOSH | 30.21 | 0 | 0 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retrofitting of existing LDS under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase- V) | Assistant Engineer,HQ | Junior Engineer | ORD/000132/2021-2022 | 1441/JD | 09/09/2021 | 09/10/2021 | RAGHU DAS | 31.64 | 0 | 0 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Laying distribution system Mogalkata Tea Garden Area Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Part-F)" |  |  | ORD/000201/2019-2020 | 1146/JD | 25/10/2019 | 24/11/2019 | PRADIP KR SEN | 5.53 | 1.01 | 18.33 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including Retrofitting with Jal Sapna under the command area of Husludanga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000233/2022-2023 | 1906/JD | 27/09/2022 | 22/10/2022 | SWAPAN SAHA | 17.2 | 14.03 | 81.56 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Retrofittings works in connection with Functional House Hold Tap connection and 4th Pump House under "JAL JEEVAN MISSION " for Boloram, Bandhurngar ,Vandarigacch of Ambari Falakata Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2022-2023 | 702/JD | 17/03/2023 | 01/05/2023 | SUBIR GHOSH | 52.54 | 0 | 0 | 20
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC BARADIGHI WORK |  |  | VCH/000288/2022-2023 | BP-2022-23-115 | 17/08/2022 |  | PRIYABRATA KARMAKAR | 4.6 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC SAMSING TG |  |  | VCH/000289/2022-2023 | BP-2022-23-116 | 18/08/2022 |  | PINTU DAS | 4.75 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC KILKOTE |  |  | VCH/000290/2022-2023 | BP-2022-23-118 | 18/08/2022 |  | VEDATRAYEE AND CO. | 1.11 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC FOR LUKSHAN BAZAR . |  |  | VCH/000311/2022-2023 | BP-2022-23-89 | 02/08/2022 |  | ANUP SARKAR | 24.13 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | fhtc for ambari falakata |  |  | VCH/000463/2021-2022 | null | 21/10/2021 |  | NARAYAN SARKAR | 23.7 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | LDS AMBARI FALAKATA PWSS |  |  | VCH/000479/2021-2022 | null | 29/10/2021 |  | GOURAB GUHA ROY | 4.72 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | AMBARIFALAKATA FHTC |  |  | VCH/000796/2021-2022 | BP-2021-22-88 | 01/11/2021 |  | NARAYAN SARKAR | 23.7 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | ambarifalakata fhtc |  |  | VCH/000810/2021-2022 | BP-2021-22-98 | 16/11/2021 |  | GOURAB GUHA ROY | 4.72 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | AMBARI FALAKATA |  |  | VCH/001051/2021-2022 | BP-2021-22-186 | 14/01/2022 |  | RAGHU DAS | 31.53 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Songachi Tea Garden piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. (PART-C) |  |  | VCH/001154/2021-2022 | BP-2021-22-272 | 22/02/2022 |  | R.S CONSTRUCTION | 13.45 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Songachi T.G. piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. (PART-D) |  |  | VCH/001155/2021-2022 | BP-2021-22-271 | 22/02/2022 |  | R.S CONSTRUCTION | 5.04 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC AMBARI FALAKATA |  |  | VCH/001197/2021-2022 | BP-2021-22-329 | 28/02/2022 |  | SAPTASWA SARKAR | 21.58 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC DAKSHIN SALBARI |  |  | VCH/001254/2021-2022 | BP-2021-22-409 | 23/03/2022 |  | SAHA CONSTRUCTION | 4.8 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC PURBADURAMARI |  |  | VCH/001263/2021-2022 | BP-2021-22-465 | 27/03/2022 |  | SIBU DEY | 28.4 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC PATKIDAHA |  |  | VCH/001380/2021-2022 | BP-2021-22-544 | 31/03/2022 |  | PRABIR SHOME | 5.89 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC JOGESH CH T.G |  |  | VCH/001391/2021-2022 | BP-2021-22-535 | 31/03/2022 |  | SANDIP BANIK | 19.98 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | FHTC RAIPUR T.G |  |  | VCH/001406/2021-2022 | BP-2021-22-549 | 31/03/2022 |  | ANUP KUMAR KUNDU | 2.19 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block | SM/08036 | Retrofitting | RETROFITTING WORK FOR DAKSHIN SHALBARI |  |  | VCH/001436/2021-2022 | BP-2021-22-409 | 23/03/2022 |  | SAHA CONSTRUCTION | 4.8 | 0 | 0 | 0
Total | [13 empty] | 385.16 | 29.17 | 7.57