## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of CHAKIAVITA piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000020/2021-2022 | 754/JD | 13/05/2021 | 03/06/2021 | ANUP SARKAR | 23.75 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chakiavita Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000100/2021-2022 | 1339/JD | 23/08/2021 | 22/09/2021 | PRADIP SAHA | 30.16 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chakiavita Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase- III) | Assistant Engineer,HQ | Junior Engineer | ORD/000110/2021-2022 | 1404/JD | 03/09/2021 | 03/10/2021 | SAPTASWA SARKAR | 30.86 | 0 | 0 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna within the area of Chakiavita and Kamarvita village under the command area of Chakiavita piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000270/2021-2022 | 2045/JD | 07/12/2021 | 28/12/2021 | BARUN KUMAR DUTTA | 39.68 | 0 | 0 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | Retrofitting works in connection with Functional House Hold Tap connection under "JAL SWAPNA" for Baniapara of Chakiavita Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000283/2021-2022 | 1827/JD | 18/11/2021 | 09/12/2021 | JAYDEB SAHA | 11.32 | 0 | 0 | 1
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | Retrofitting works related to FHTC inconnection with Jalsapna at different locations of Chanadipa and Madhya Salbari Mouza of Dakshin Salbari water Supply Scheme under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer 2 | ORD/000518/2021-2022 | 163/RWS | 28/02/2022 | 15/03/2022 | NARAYAN SARKAR | 4.47 | 4.49 | 100.49 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC ENGO |  |  | VCH/000324/2021-2022 | null | 01/10/2021 |  | BIMAN DAS | 2.2 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC CHAKIAVITA |  |  | VCH/000472/2021-2022 | null | 29/10/2021 |  | PRADIP SAHA | 25.87 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | RETREOFITTING WORK FOR BOAL MARI |  |  | VCH/000476/2021-2022 | null | 29/10/2021 |  | KANAI LAL SEN | 9.37 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | RETROFITTING WORK FOR ARAGI GORALBARI |  |  | VCH/000483/2021-2022 | null | 29/10/2021 |  | NARAYAN CHAKRABORTY | 4.84 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | RETROFITTING WORK FOR ARAJI GORALBARI PWSS |  |  | VCH/000484/2021-2022 | null | 29/10/2021 |  | SAPTASWA SARKAR | 11.02 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | CHAKIAVITA FHTC |  |  | VCH/000797/2021-2022 | BP-2021-22-111 | 16/11/2021 |  | SAPTASWA SARKAR | 4.86 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC CHAKIAVIT |  |  | VCH/000798/2021-2022 | BP-2021-22-110 | 16/11/2021 |  | SAPTASWA SARKAR | 1.79 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC CHAKIAVITA |  |  | VCH/000799/2021-2022 | BP-2021-22-109 | 16/11/2021 |  | SAPTASWA SARKAR | 4.37 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC CHAKIAVITA |  |  | VCH/000800/2021-2022 | BP-2021-22-112 | 16/11/2021 |  | NARAYAN CHAKRABORTY | 4.84 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | fhtc chakiavita |  |  | VCH/000801/2021-2022 | BP-2021-22-99 | 16/11/2021 |  | PRADIP SAHA | 25.87 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | fhtc chakiavita |  |  | VCH/000808/2021-2022 | BP-2021-22-95 | 16/11/2021 |  | KANAI LAL SEN | 4.59 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | fhtc chakiavita |  |  | VCH/000809/2021-2022 | BP-2021-22-96 | 16/11/2021 |  | KANAI LAL SEN | 4.78 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | CHAKIAVITA |  |  | VCH/000922/2021-2022 | BP-2021-22-116 | 03/12/2021 |  | SAPTASWA SARKAR | 3.98 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC CHAKIAVITA |  |  | VCH/001096/2021-2022 | BP-2021-22-167 | 14/01/2022 |  | SAPTASWA SARKAR | 29.39 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC JITI |  |  | VCH/001185/2021-2022 | BP-2021-22-280 | 23/02/2022 |  | CALCON CONSTRUCTIONS | 22.07 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC MADHYA KHUTTIMARI |  |  | VCH/001187/2021-2022 | BP-2021-22-280 | 23/02/2022 |  | KAMALESH SEN | 9.42 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC CHAKIAVITA |  |  | VCH/001200/2021-2022 | BP-2021-22-330 | 28/02/2022 |  | BARUN KUMAR DUTTA | 32.95 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC RIABARI |  |  | VCH/001251/2021-2022 | BP-2021-22-394 | 22/03/2022 |  | SAPTASWA SARKAR | 5.63 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC RIABARI TG PWSS (PHASE-II) |  |  | VCH/001294/2021-2022 | BP-2021-22-394 | 22/03/2022 |  | SAPTASWA SARKAR | 5.63 | 0 | 0 | 0
26 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC NAKHATI T.G PWSS |  |  | VCH/001302/2021-2022 | BP-2021-22-348 | 08/03/2022 |  | R.S CONSTRUCTION | 4.81 | 0 | 0 | 0
27 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC JOGESH CHANDRA T.G PWSS |  |  | VCH/001350/2021-2022 | BP-2021-22-357 | 09/03/2022 |  | M/S SURAJIT DEY AND CO. | 28.14 | 0 | 0 | 0
28 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC BHANGAMALI WSS |  |  | VCH/001358/2021-2022 | BP-2021-22-496 | 29/03/2022 |  | RABINDRANATH DUTTA | 16.94 | 0 | 0 | 0
29 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | CONST RCC JURANTI T.G |  |  | VCH/001365/2021-2022 | BP[-2021-22-463 | 27/03/2022 |  | DIPAK KUMAR CHAKRABORTY | 3.43 | 0 | 0 | 0
30 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC BARADIGHI PWSS |  |  | VCH/001366/2021-2022 | BP-2021-22-476 | 28/03/2022 |  | DIPAK KUMAR CHAKRABORTY | 41.29 | 0 | 0 | 0
31 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block | SM/08285 | Retrofitting | FHTC AWC IN MAYNAGURI BLOCK |  |  | VCH/001389/2021-2022 | BP-2021-22-502 | 30/03/2022 |  | DREAM CONSTRUCTION | 4.84 | 0 | 0 | 0
Total | [13 empty] | 453.16 | 4.49 | 0.99