## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Sinking of Two No. 183 mm x 125mm dia 120 m Deep Tube well by ODEX-165 drilling Method, at Indong TG area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000074/2022-2023 | 1313/JD | 16/06/2022 | 16/07/2022 | S. N. POLYMERS PVT. LTD. | 13.84 | 13.47 | 97.31 | 0
2 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Laying distribution system (Phase - II) & Rising Main for Ingdong Tea Garden piped water supply scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000137/2023-2024 | 705/JD | 13/07/2023 | 03/08/2023 | KANAI LAL SEN | 21.42 | 21.73 | 101.47 | 100
3 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Construction of Pump House (5.40 m X 3.60 m) size with Sanitary & Plumbing arrangement at Head Works Site for Indong Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2022-2023 | 856/JD | 01/04/2022 | 31/05/2022 | SUJOY CHOWDHURY | 5.61 | 5.61 | 100 | 0
4 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Laying distribution system including Providing Functional Household Tap Connection in connection with Jal Swapna for Indong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000566/2021-2022 | 690/JD | 15/03/2022 | 13/06/2022 | KANAI LAL SEN | 112.93 | 57.63 | 51.03 | 85
5 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Soil Investigation work for 200 CuM Over Head Reservoir (OHR) at Indong T.G. Area P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000695/2021-2022 | 1068/JSSD | 25/01/2022 | 14/02/2022 | MOYTEC | 2.02 | 2.02 | 100 | 0
6 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Construction of 200 Cum OHR as per Departmental Design & Drawing for INDONG Tea Garden Area Piped Water Supply Scheme Block : Matiali District- Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000697/2021-2022 | 472/JD | 21/02/2022 | 20/08/2022 | M/S SIBU DEY AND CO. | 54.95 | 49.29 | 89.71 | 100
7 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Construction of Pump House (3.60m x 2.40m) size with Sanitary & Plumbing arrangement at 2nd Tube well site for Indong T.G. area of P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000709/2021-2022 | 1043/JSSD | 24/01/2022 | 10/03/2022 | ABHISEK KUNDU | 4.63 | 4.63 | 100 | 0
8 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Construction of boundary wall with gate, drain and pathway for 2nd tubewell site of Indong Tea Garden Area piped water supply scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001008/2021-2022 | 1039/JSSD | 21/01/2022 | 10/02/2022 | BISWAJIT MANDAL | 3.76 | 0 | 0 | 0
9 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 1064/JD | 28/04/2022 |  | Resource Division | 37.54 | 0 | 0 | 0
10 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 175/JD | 28/04/2023 |  | Resource Division | 14.68 | 0 | 0 | 0
11 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 2065/JD | 10/01/2024 |  | Resource Division | 7.61 | 0 | 0 | 0
12 | JALPAIGURI | Matiali | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Soil investigation work for 200 CUM Over head reservoir (OHR) at Indong TG |  |  | VCH/000365/2022-2023 | null | 27/09/2022 |  | MOYTEC | 1.01 | 0 | 0 | 0
13 | JALPAIGURI | Matiali | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for INDONG TG AREA PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000771/2022-2023 | 77/NMD | 27/01/2023 | 26/02/2023 | B.B. CONCERNED | 10.86 | 10.86 | 100 | 100
14 | JALPAIGURI | Matiali | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for INDONG TG AREA PWSS, TW no II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000772/2022-2023 | 78/NMD | 27/01/2023 | 26/02/2023 | ALPHA ENTERPRISE | 10.86 | 10.59 | 97.51 | 100
15 | JALPAIGURI | Matiali | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | New Service Connection Charge for INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 4002964298, Reference ID :402851947] |  |  | VCH/000971/2022-2023 | BP/22-23/89 | 01/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
16 | JALPAIGURI | Matiali | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Installation of Infrastructure COST at INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 100000059409, Reference ID : 860248999] |  |  | VCH/000972/2022-2023 | BP/22-23/89 | 01/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.22 | 0 | 0 | 0
17 | JALPAIGURI | Matiali | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | New Service Connection Charge for INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 4002964293, Reference ID :402851944] |  |  | VCH/000973/2022-2023 | BP/22-23/89 | 01/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
18 | JALPAIGURI | Matiali | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 | New | Installation of Infrastructure COST at INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 100000059407, Reference ID : 860248997] |  |  | VCH/000974/2022-2023 | BP/22-23/89 | 01/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.55 | 0 | 0 | 0
Total | [13 empty] | 307.85 | 175.83 | 57.12