## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Emergency water supply arrangement to the dengue effected area related to Bagrakote water supply Scheme for 45 days . ( from 29.06.2022 to 12.08.2022) | Assistant Engineer | Junior Engineer | ORD/000299/2022-2023 | 437/RWS | 07/07/2022 | 21/08/2022 | SWAPAN SAHA | 4.47 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of Boundary wall, drain and pathway for 2nd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000349/2022-2023 | 134/JD | 17/01/2023 | 16/02/2023 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.01 | 3.22 | 45.94 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Sinking of 3 Nos. Tubewell by ODEX-165 method for Bagrakote W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 1516/JD | 16/10/2023 | 15/11/2023 | RANJEET SINGH BENIWAL | 20.54 | 16.66 | 81.13 | 100
4 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Laying Distribution system and functional household tap connection for Bagrakote Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000378/2021-2022 | 351/JD | 03/02/2022 | 04/05/2022 | M/S GARGO TRADERS | 184.25 | 24.16 | 13.11 | 38
5 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | SOIL INVESTIGATION WORK FOR BAGRAKOTE T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000398/2021-2022 | 852/RWS | 03/12/2021 | 18/12/2021 | G. TECH INDIA | 2.03 | 1.63 | 80.55 | 1
6 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000433/2023-2024 | 1674/JD | 24/11/2023 | 08/01/2024 | KAPIL MANI BRAHMAN | 11.66 | 7.58 | 65.02 | 100
7 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. .(H/W Site) .(4th Call) |  |  | ORD/000438/2023-2024 | 1275/RWS | 24/11/2023 | 08/12/2023 | RANJEET SINGH BENIWAL | 1.37 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(2nd Site) .(4th Call) |  |  | ORD/000439/2023-2024 | 1274/RWS | 24/11/2023 | 08/12/2023 | RANJEET SINGH BENIWAL | 0.8 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of 400 CuM Capacity R.C.C. Over Head Reservoir (OHR) of 20 Mtr Staging Height at Bagrakote Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000590/2023-2024 | 2410/JD | 19/02/2024 | 17/08/2024 | D.C RAKSHIT AND SONS INDIA PRIVATE LTD. | 106.62 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Construction of Pump House (5.40m x 3.60m) Head work site with sanitary & plumbing arrangement including Rising main interconnection and restoration work at Bagrakote Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000726/2023-2024 | 2486/JD | 27/02/2024 | 12/04/2024 | GARGO TRADERS | 15.46 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 1940/JD | 02/12/2021 |  | Resource Division | 12.32 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 172/JD | 28/04/2023 |  | Resource Division | 82.59 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 2068/JD | 10/01/2024 |  | Resource Division | 14.15 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | New Service Connection Charge for BAGRAKOTE TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266408, Reference ID : 403105530] |  |  | BILL/01269/2023-2024 | BP/23-24/150 | 05/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 100000093885, Reference ID : 860285545] |  |  | BILL/01270/2023-2024 | BP/23-24/151 | 05/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.98 | 0 | 0 | 0
16 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093777, Reference ID : 860285647] |  |  | BILL/01272/2023-2024 | 23-24/152&161 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0 | 0
17 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | New Service Connection Charge for BAGRAKOTE TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266397, Reference ID : 403105521] |  |  | BILL/01273/2023-2024 | 23-24/152&161 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
18 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093883, Reference ID : 860285543] |  |  | BILL/01274/2023-2024 | 23-24/152&161 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.39 | 0 | 0 | 0
19 | JALPAIGURI | Mal | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BAGRAKOTE TEA GARDEN AREA PWSS,at TW NO I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000635/2023-2024 | 1481/NMD | 17/08/2023 | 16/09/2023 | SUBHRA ENTERPRISE | 41.17 | 15.82 | 38.42 | 25
Total | [13 empty] | 518.35 | 69.07 | 13.33