## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Dwarikamari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000138/2022-2023 | 1442/JD | 20/07/2022 | 03/09/2022 | SADHAN KARMAKAR | 15.34 | 13.83 | 90.17 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. at 4th tube well site of Rejuvenation of Dwarikamari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000141/2022-2023 | 1447/JD | 20/07/2022 | 03/09/2022 | SADHAN KARMAKAR | 15.34 | 14.29 | 93.14 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Shifting of Pipeline damaged due to construction of Rest area and Truck lay bye by the NHAI in between Maynaguri BDO Office and Tekatuli for Dwarikamari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000198/2022-2023 | 1739/JD | 08/09/2022 | 29/09/2022 | BARUN KUMAR DUTTA | 6.49 | 6.29 | 96.95 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Dwarikamari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000273/2022-2023 | 2010/JD | 01/11/2022 | 16/11/2022 | ABHIJIT SARKAR | 5.77 | 4.43 | 76.73 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Dwarikamari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000466/2021-2022 | 2285JD | 31/12/2021 | 30/01/2022 | SUBRATA GOSWAMI | 17.42 | 3.61 | 20.75 | 1
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Dwarikamari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000483/2021-2022 | 2216/JD | 27/12/2021 | 25/02/2022 | BARUN KUMAR DUTTA | 11.45 | 11.47 | 100.18 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Dwarikamari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000484/2021-2022 | 2217/JD | 27/12/2021 | 25/02/2022 | PINTU DAS | 11.44 | 11.42 | 99.8 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | TUBE WELL BILL |  |  | VCH/001151/2021-2022 | BP-2021-22-266 | 16/02/2022 |  | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 45.75 | 0 | 0 | 0
9 | JALPAIGURI |  | Central Drilling | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF DWARIKAMARI (TW-I) PWSS UNDER CDD, PHE DTE. |  |  | ORD/000178/2021-2022 | 722/ CDD | 05/10/2021 | 04/11/2021 | PADMA ENGINEERING & CO. | 10.57 | 9.53 | 90.15 | 0
10 | JALPAIGURI |  | Central Drilling | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF DWARIKAMARI (TW-II) PWSS UNDER CDD, PHE DTE. |  |  | ORD/000180/2021-2022 | 739/ CDD | 07/10/2021 | 06/11/2021 | PADMA ENGINEERING & CO. | 10.57 | 7.61 | 71.98 | 0
11 | JALPAIGURI |  | Central Drilling | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | ADDITIONAL MOBILISATION OF ALL MACHINERIES & ACCESSORIES INCLUDING LOADING & UNLOADING FROM STORE TO DRILLING SITE DWARIKAMARI (TW-I) PWSS. |  |  | ORD/000183/2021-2022 | 457/CMSD-II (D) | 08/10/2021 | 18/10/2021 | PADMA ENGINEERING & CO. | 0.46 | 0.37 | 80 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for augmentation of DWARIKAMARI W/S Scheme at T/W No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2022-2023 | 205/NMD | 04/04/2022 | 25/04/2022 | PRATIK ROY | 2.16 | 2.16 | 100 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for augmentation of DWARIKAMARI W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2022-2023 | 204/NMD | 04/04/2022 | 25/04/2022 | M/S ANJALI ENTERPRISE | 2.16 | 2.16 | 100 | 0
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of DWARIKAMARI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000009/2022-2023 | 277/NMD | 26/04/2022 | 26/05/2022 | M/S PARITOSH BHOWMICK AND CO. | 8.37 | 8.37 | 100 | 0
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of DWARIKAMARI PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000010/2022-2023 | 278/NMD | 26/04/2022 | 26/05/2022 | SUMON ELECTRICAL | 8.35 | 8.35 | 100 | 0
16 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000014/2024-2025 | 827/HQ/NMD | 30/04/2024 | 29/07/2024 | UTTAM PAUL | 0.95 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000197/2024-2025 | 1306/HQ/NMD | 31/07/2024 | 29/10/2024 | UTTAM PAUL | 0.95 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000985/2023-2024 | 1734/HQ/NMD | 30/10/2023 | 30/01/2024 | UTTAM PAUL | 0.95 | 0.93 | 98.57 | 100
19 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001137/2023-2024 | 430/HQ/NMD | 31/01/2024 | 30/04/2024 | UTTAM PAUL | 0.95 | 0 | 0 | 0
20 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | Infrastructure cost for New Service Connection Charge for T/W No. III of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 100000052514, Reference ID : 860241674 |  |  | VCH/000251/2022-2023 | BP/2022-23/21 | 23/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.4 | 0 | 0 | 0
21 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | New Service Connection Charge for T/W No. IV of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 4002932370, Reference ID : 402825217 |  |  | VCH/000252/2022-2023 | BP/2022-23/21 | 23/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
22 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. | SM/09459 | Augmentation | New Service Connection Charge for T/W No. III of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 4002932367, Reference ID : 402825216 |  |  | VCH/000253/2022-2023 | BP/2022-23/21 | 23/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
Total | [13 empty] | 180.18 | 104.81 | 58.17