## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF KILKOT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, Block- Matiali, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000377/2021-2022 | 350/JD | 03/02/2022 | 03/06/2022 | NARENDRA KUMAR | 57.75 | 13.4 | 23.2 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | Construction of boundary wall with gate,drain, Pipe line for H/W site of KILLKOTE T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000562/2020-2021 | 202/JD | 10/02/2021 | 12/03/2021 | M/S SURAJIT DEY AND CO. | 14.94 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | soil test for kilkote |  |  | VCH/000239/2022-2023 | bp2022-23- | 14/06/2022 |  | G. TECH INDIA | 2.03 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | CONST OF RISING MAIN CONNECTION FOR KILKOTE T.G |  |  | VCH/000240/2022-2023 | bp2022-23-49 | 07/06/2022 |  | GOUR KUMAR MITRA | 4.8 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | OHR KILKOTE |  |  | VCH/000272/2022-2023 | BP-2022-23-80 | 28/07/2022 |  | NARENDRA KUMAR | 2.61 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | KILKOTE |  |  | VCH/001077/2021-2022 | BP-2021-22-196 | 19/01/2022 |  | M/S SURAJIT DEY AND CO. | 14.98 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | FHTC KILKOTE |  |  | VCH/001201/2021-2022 | BP-2021-22-328 | 28/02/2022 |  | M/S SURAJIT DEY AND CO. | 11.92 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | RETRO FITTING WORK HOPE |  |  | VCH/001202/2021-2022 | BP-2021-22-327 | 28/02/2022 |  | UMWELT ENGINEER PRIVATE LIMITED | 0.7 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | INSTALLATION IRON ELIMINATION PLANT |  |  | VCH/001288/2021-2022 | BP-2021-22-519 | 30/03/2022 |  | MONDAL PRECISION PRIVATE LIMITED | 5.1 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | SOIL INVESTIGATION BHUSKA DANGA PWSS |  |  | VCH/001305/2021-2022 | BP-2021-22-424 | 25/03/2022 |  | MABCO CONSULTANT | 2.01 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | SOIL INVESTIGATION WORK KILKOTE T.G |  |  | VCH/001318/2021-2022 | BP-2021-22-436 | 26/03/2022 |  | MABCO CONSULTANT | 2.01 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | CONST 250 M3REJ KILKOTE T.G PWSS |  |  | VCH/001325/2021-2022 | BP-2021-22-368 | 16/03/2022 |  | NARENDRA KUMAR | 23.58 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. | SM/09461 | Augmentation | CONST BLOWER ROOM PURBA DURAMARI WSS |  |  | VCH/001368/2021-2022 | BP-2021-22-520 | 30/03/2022 |  | MONDAL PRECISION PRIVATE LIMITED | 5.78 | 0 | 0 | 0
Total | [13 empty] | 148.2 | 13.4 | 9.04