## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Supply of fuel against vehicle WB-71B-3112 under Assistant Engineer Jalpaiguri Sadar Sub-Division PHE Dte for the month April 2023 |  |  | BILL/00208/2023-2024 | BP-2023-24-116 | 01/06/2023 |  | FILL & SMILE | 0.26 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | Assistant Engineer | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 09/07/2023 | APIKUL ALI | 1.76 | 0.36 | 20.54 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) | Assistant Engineer | Junior Engineer | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 09/07/2023 | RAKESH SARKAR | 1.76 | 0.34 | 19.41 | 0.5
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Supplying, Erecting, Installation and Commissioning of Iron Elimination Plant (I.E.P.) (15 cum 2 Unit) at 3rd site and 4th site of Chakiavita Piped Water Supply Scheme at Block - Rajganj under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000509/2023-2024 | 1776/JD | 08/12/2023 | 06/02/2024 | SANDIP BANIK | 25.78 | 15.91 | 61.7 | 90
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Chakiavita P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000533/2021-2022 | 131/JD | 14/01/2022 | 15/03/2022 | SUKUMAR KUNDU | 4.65 | 4.65 | 100 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Rejuvenation of Chakiavita PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000558/2021-2022 | 452/JD | 18/02/2022 | 20/03/2022 | MECHANO TRADING CO. | 7.79 | 7.36 | 94.52 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 4th Tube well for Rejuvenation of Chakiavita PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000559/2021-2022 | 453/JD | 18/02/2022 | 20/03/2022 | MECHANO TRADING CO. | 7.79 | 6.18 | 79.32 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Chakiavita P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000577/2021-2022 | 143/JD | 18/01/2022 | 19/03/2022 | PRIYABRATA KARMAKAR | 4.65 | 4.65 | 100 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 3rd tubewell at Chakiavita piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000605/2023-2024 | 2306/JD | 07/02/2024 | 08/03/2024 | SUKUMAR KUNDU | 8.82 | 4.06 | 46.07 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell at Chakiavita piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000606/2023-2024 | 2307/JD | 07/02/2024 | 08/03/2024 | PRIYABRATA KARMAKAR | 9.03 | 8.72 | 96.58 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | RETROFITTING WORKS SAMSING T.G |  |  | VCH/001269/2021-2022 | BP-2021-22-518 | 30/03/2022 |  | SUJAN LAMA | 11.66 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | New Service Connection Charge for CHAKIABHITA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 4003135861 ; Reference ID : 403001371] |  |  | BILL/00010/2023-2024 | BP/23-24/06 | 03/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Infrastructure Cost for CHAKIABHITA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 100000076456 ; Reference ID : 860267596] |  |  | BILL/00011/2023-2024 | BP/23-24/06 | 03/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.65 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Supply, delivery & installation of 30 KVA Servo Motor operated Copper wound line voltage corrector Chakiabhita W/S Scheme, TW No. I in the dist. of Jalpaiguri under NMD PHE Dte. |  |  | ORD/000392/2020-2021 | 1905/NMD | 07/01/2021 | 06/02/2021 | MAA DURGA CONCERN | 3.03 | 3.03 | 100 | 0
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for CHAKIABHITA (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000582/2022-2023 | 1121/NMD | 12/09/2022 | 12/10/2022 | CHOWDHURY AND BASU ENTERPRISE | 7.95 | 7.67 | 96.44 | 100
16 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF CHAKIABHITA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000752/2022-2023 | 52/NMD | 24/01/2023 | 23/02/2023 | M/S B.ENTERPRISE | 11.67 | 4.87 | 41.74 | 100
17 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under CHAKIABHITA (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000778/2022-2023 | 99/NMD | 03/02/2023 | 24/02/2023 | CHOWDHURY AND BASU ENTERPRISE | 2.52 | 2.52 | 100 | 100
18 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | New Service Connection Charge for TW-III, of CHAKIAVITA W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951612,Reference ID : 860244515 |  |  | VCH/000315/2022-2023 | BP/2022-23/31 | 16/08/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme | SM/09482 | Augmentation | Infrustructure cost for New Service Connection Charge for TW-III, of CHAKIAVITA W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054735,Reference ID : 402843365 |  |  | VCH/000316/2022-2023 | BP/2022-23/31 | 16/08/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.79 | 0 | 0 | 0
Total | [13 empty] | 121.99 | 70.33 | 57.65