## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Replacement of existing defunct sluice valve for Gairkata Water Supply Scheme at Banarhat Development block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000027/2023-2024 | 127/JD | 28/04/2023 | 05/05/2023 | SHANTI CONSTRUCTION | 1.66 | 1.49 | 89.31 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation Gairkata P.W.S.S under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000049/2022-2023 | 1191/JD | 20/05/2022 | 04/07/2022 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.65 | 2.32 | 50 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Laying Distribution System including providing CI/DI Rising Main connection and providing FHTC in connection with JJM for Augmentation of Gairkata Piped Water Supply Scheme at Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000442/2022-2023 | 695/JD | 17/03/2023 | 15/06/2023 | M/S R.N. TRADERS | 333.21 | 40.4 | 12.13 | 8
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Rejuvenation of different components of PWSS of Over Head Reservoir site at Gairkata Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000546/2023-2024 | 1974/JD | 03/01/2024 | 17/02/2024 | APEX ENGINEERING | 22.45 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Gairkata PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000563/2021-2022 | 455/JD | 18/02/2022 | 11/03/2022 | MAA ENTERPRISES | 7.93 | 2.85 | 35.99 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 554/JD | 01/03/2022 |  | Resource Division | 14.26 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003196195, Reference ID : 403048167] |  |  | BILL/00569/2023-2024 | BP/23-24/70 | 09/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.42 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W I, under DHUPGURI CCC [APPLICATION NO. 4003208335 ; Reference ID : 403057217] |  |  | BILL/00990/2023-2024 | BP/23-24/93 | 29/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme | SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W II, under DHUPGURI CCC [APPLICATION NO. 4003208338 ; Reference ID : 403057218] |  |  | BILL/00991/2023-2024 | BP/23-24/93 | 29/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
Total | [13 empty] | 395.96 | 47.07 | 11.89