## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme | SM/10043 | Augmentation | Construction of Pump House (5.40 m X 3.60 m) size with sanitary & plumbing arrangement at head works site for Jalapara PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000025/2023-2024 | 126/JD | 28/04/2023 | 12/06/2023 | EDIFICE ENTERPRISE | 5.91 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme | SM/10043 | Augmentation | Construction of 250 CuM Over Head Reservoir (OHR) (Staging height 20 Mtr.) as per departmental design and drawing for Augmentation of Jalapara Piped Water Supply Scheme at Block - Dhupguri in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000139/2023-2024 | 700/JD | 13/07/2023 | 09/01/2024 | M/S. D.K. DEY & CO.. | 78.88 | 8.19 | 10.39 | 20
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme | SM/10043 | Augmentation | Retrofiting works i.c.w.FHTC under Jalsapna including repair of damaged pipe lines during road construction at different areas under Dakshin Salbari Piped W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000175/2022-2023 | 553/RWS | 01/09/2022 | 01/10/2022 | NEW KUNDU ENTERPRISE | 3.16 | 3.14 | 99.27 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme | SM/10043 | Augmentation | Laying Distribution System for Augmentation of Jalapara Piped Water Supply Scheme at Nagrakata & Dhupguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000286/2023-2024 | 1413/JD | 03/10/2023 | 01/01/2024 | BOSE ENTERPRISE | 256.04 | 87.97 | 34.36 | 25
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme | SM/10043 | Augmentation | Construction of different balance components of Jalapara PWSS in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000829/2023-2024 | 2757/JD | 15/03/2024 | 14/04/2024 | ANUP KUMAR KUNDU | 88.77 | 0 | 0 | 5
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme | SM/10043 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 54/JD | 09/04/2024 |  | Resource Division | 114.02 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Augmentation of Jalapara Piped Water Supply Scheme | SM/10043 | Augmentation | New Service Connection Charge for AUGMENTATION OF JALAPARA, T/W-I, under BANARHAT CCC APPLICATION NO. 4003418441 Reference ID : 403225407 |  |  | BILL/00368/2024-2025 | BP/24-25/73 | 30/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.58 | 0 | 0 | null
8 | JALPAIGURI |  | Northern Mechanical | Augmentation of Jalapara Piped Water Supply Scheme | SM/10043 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF JALAPARA PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000871/2022-2023 | 335/NMD | 29/03/2023 | 28/04/2023 | MUSTAFI CONCERN | 21.8 | 0 | 0 | 0
Total | [13 empty] | 577.16 | 99.3 | 17.2