## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | Augmentation | Laying of New Pipeline adjacent to the National Highway for implementation of Jalswapa programme along with minor retrofitting works(laying of parallel line)within the command area of Devpara T.G.P.W.S.S under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000162/2022-2023 | 1448/JD | 20/07/2022 | 04/08/2022 | JAYDEB SAHA | 4.85 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | Augmentation | Minor Repairing of Distribution System along with FHTC works under Jalswapna Programme along with other retrofitting works ,chokage removal alog ,repairing of partially damaged C.I.D.F delivery main with other ancillary works within the command area of Devpara T.G.P.W.S.S under Jalpaiguri Division, P.H.E.Dte.(Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000216/2022-2023 | 1806/JD | 14/09/2022 | 05/10/2022 | JAYDEB SAHA | 4.84 | 4.85 | 100.2 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | Augmentation | Construction of One no Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Rejuvenation of Debpara TG Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000276/2023-2024 | 1268/JD | 13/09/2023 | 28/10/2023 | BOSE ENTERPRISE | 17.67 | 2.45 | 13.87 | 20
4 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | Augmentation | Laying distribution system with for Rejuvenation of Debpara T.G. Piped water Supply Scheme at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000341/2023-2024 | 1348/JD | 26/09/2023 | 26/10/2023 | JAYDEB SAHA | 30.19 | 12.09 | 40.06 | 70
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | Augmentation | Sinking of five nos Tube Well by Odex- 165 method of drilling at different Tube Well site in connection with jal jeevan mission under Augmentation/Rejuvenation of Kathalguri TG PWSS (Two Nos), Devpara TG PWSS (One No), Banarhat Bazar PWSS (One No), Sajna Para PWSS (One No) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2023-2024 | 1520/JD | 16/10/2023 | 30/11/2023 | ROY ENGINEERS | 41.28 | 0 | 0 | 100
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | Augmentation | New Service Connection Charge for DEBPARA TEA GARDEN, T/W III, under BANARHAT CCC [APPLICATION NO. 4003193586 ; Reference ID : 403045949] |  |  | BILL/00997/2023-2024 | BP/23-24/96 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | Augmentation | Infrastructure Cost for DEBPARA TEA GARDEN, T/W III, under BANARHAT CCC [APPLICATION NO. 100000083812 ; Reference ID : 860275312] |  |  | BILL/00998/2023-2024 | BP/23-24/96 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.2 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/11812 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DEBPARA TG PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000453/2023-2024 | 1392/NMD | 09/08/2023 | 08/09/2023 | UTTAM PAUL | 12.15 | 0 | 0 | 60
Total | [13 empty] | 113.86 | 19.4 | 17.04