## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Construction of different components of Amguri PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc.i.c.w. Jal Jeevan Missionat Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/000011/2023-2024 | 29/JD | 10/04/2023 | 07/10/2023 | SUKES BASU MAJUMDAR | 514.99 | 170.27 | 33.06 | 50
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-C of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000070/2024-2025 | 985/JD | 14/08/2024 | 29/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 4.63 | 0 | 0 | 0
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Construction of Boundary Wall at 2nd Pump House site Including raising main and interconnection of Amguri PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000674/2023-2024 | 165/RWS | 15/02/2024 | 16/03/2024 | DEEP CONSTRUCTION | 6.17 | 3.08 | 49.94 | 100
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of Amguri PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000814/2023-2024 | 2631/JD | 07/03/2024 | 21/04/2024 | B.M CONSTRUCTION | 16.14 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 151/JD | 28/04/2023 |  | Resource Division | 105.47 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 2056/JD | 09/01/2024 |  | Resource Division | 14.62 | 0 | 0 | 0
7 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | New Service Connection Charge for AMGURI, T/W No. I, under MAYNAGURI CCC, [APPLICATION NO. 4003266414, Reference ID : 403108583] |  |  | BILL/01283/2023-2024 | 23-24/155&163 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.24 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | New Service Connection Charge for AMGURI, T/W No. II, under MAYNAGURI CCC [APPLICATION NO. 4003297950 , Reference ID : 403128266] |  |  | BILL/01780/2023-2024 | BP/23-24/217 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.49 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AMGURI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000843/2022-2023 | 271/NMD | 21/03/2023 | 20/04/2023 | TALUKDER ENTERPRISE | 22.92 | 10.91 | 47.62 | 50
Total | [13 empty] | 695.65 | 184.26 | 26.49