## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Construction of different components of Madhya Daukimari PWSS i.e TW, Pump Houses, Water Distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Banarhat under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000012/2023-2024 | 28/JD | 10/04/2023 | 07/10/2023 | SUKES BASU MAJUMDAR | 506.72 | 394.14 | 77.78 | 80
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000030/2024-2025 | 692/JD | 19/07/2024 | 16/11/2024 | B.M CONSTRUCTION | 50.78 | 50.78 | 100 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Dhupguri, Rajganj and Balance of Banarhat Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2024-2025 | 940/JD | 07/08/2024 | 06/10/2024 | AKG UDYOG | 25.37 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 162/JD | 28/04/2023 |  | Resource Division | 133.55 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 1879/JD | 20/12/2023 |  | Resource Division | 11.14 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Additional New Service Connection Charge for MADHYA DAUKIMARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 100000103797 Reference ID : 860296017 |  |  | BILL/00127/2024-2025 | null | 04/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | null
7 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | New Service Connection Charge for MADHYA DAUKIMARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003388992 Reference ID : 403201630 |  |  | BILL/00292/2024-2025 | null | 06/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0 | null
8 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | New Service Connection Charge for MADHYA DAUKIMARI, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003256198, Reference ID : 403097555] |  |  | BILL/01652/2023-2024 | 23-24/169&172 | 12/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.83 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Infrastructure Cost for MADHYA DAUKIMARI , T/W-I, under DHUPGURI CCC [APPLICATION NO. 4003269038 , Reference ID : 403107836] |  |  | BILL/02030/2023-2024 | BP/23-24/311 | 21/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA DAUKIMARI PWSS, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000238/2023-2024 | 1252/NMD | 31/07/2023 | 30/08/2023 | PADMA ENGINEERING CO. | 24.51 | 8.91 | 36.37 | 50
Total | [13 empty] | 776.5 | 453.84 | 58.45