## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Dhupguri, Rajganj and Balance of Banarhat Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2024-2025 | 940/JD | 07/08/2024 | 06/10/2024 | AKG UDYOG | 25.37 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Construction of different components of Uttar Altagram PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000099/2023-2024 | 351/JD | 24/05/2023 | 20/11/2023 | SUKES BASU MAJUMDAR | 446.33 | 230.21 | 51.58 | 30
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Dhupguri block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000473/2023-2024 | 1293/RWS | 29/11/2023 | 29/12/2023 | B.M CONSTRUCTION | 3.89 | 1.95 | 50 | 100
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1116/JD | 24/08/2023 |  | Resource Division | 23.05 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 1841/JD | 15/12/2023 |  | Resource Division | 11.08 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. I, under DHUPGURI CCC [APPLICATION NO. 4003332348 , Reference ID : 403156800] |  |  | BILL/01996/2023-2024 | BP/23-24/308 | 09/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.65 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003332367 , Reference ID : 403156921] |  |  | BILL/01998/2023-2024 | BP/23-24/308 | 09/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.73 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003328084 , Reference ID : 403153544] |  |  | BILL/01999/2023-2024 | BP/23-24/308 | 09/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.26 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR ALTAGRAM PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000432/2023-2024 | 1371/NMD | 09/08/2023 | 08/09/2023 | M/S SAJAHAN CHOWDHURY | 33.24 | 13.73 | 41.3 | 50
Total | [13 empty] | 557.61 | 245.89 | 44.1