## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00525/2024-2025 | BP-2024-25-297 | 14/08/2024 |  | FILL & SMILE | 0.23 | 0 | 0 | null
2 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 |  | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
3 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2024 to 30/07/2024 | Assistant Engineer | Junior Engineer | ORD/000001/2024-2025 | 022/JSSD | 30/04/2024 | 29/07/2024 | MRITYUNJAY SIKDAR | 0.44 | 0.17 | 38.31 | 70
4 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Construction of different components of Dhumpara (N) (Zone-I & II) PWSS i.e, TW Pump House , Water distribution Network, OHR, RISING MAIN , FHTC etc. I.c.w Jal Jeevan Mission at Block - Nagrakata Under Jalpaiguri Divison P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000055/2023-2024 | 262/JD | 10/05/2023 | 06/11/2023 | S. N. POLYMERS PVT. LTD. | 471.75 | 74.61 | 15.81 | 33
5 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
6 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/08/2024 to 31/10/2024 | Assistant Engineer | Junior Engineer | ORD/000113/2024-2025 | .142/2/JSSD | 29/07/2024 | 27/10/2024 | MRITYUNJAY SIKDAR | 0.44 | 0.08 | 18.64 | 0
7 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 1/11/2023-30/04/2024 | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 378/JSSD | 30/10/2023 | 27/04/2024 | MRITYUNJAY SIKDAR | 0.88 | 0.41 | 46.72 | 0
8 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Construction of Boundary Wall & Rising main with inter connection at 2nd TW & 3rd TW site of Dhumpara(Zone -II) PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000803/2023-2024 | 570/JSSD | 05/03/2024 | 19/04/2024 | ARUP SARKAR | 8.23 | 4.15 | 50.46 | 100
9 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 163/JD | 28/04/2023 |  | Resource Division | 44.06 | 0 | 0 | 0
10 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 2055/JD | 09/01/2024 |  | Resource Division | 14.08 | 0 | 0 | 0
11 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | New Service Connection Charge for DHUMPARA, T/W No. I, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321209 ; Reference ID : 403147529] |  |  | BILL/01846/2023-2024 | BP/23-24/299 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.95 | 0 | 0 | 0
12 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | New Service Connection Charge for DHUMPARA, T/W No. II, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321417 ; Reference ID : 403147621] |  |  | BILL/01847/2023-2024 | BP/23-24/300 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
13 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | New Service Connection Charge for DHUMPARA, T/W No. III, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321422 ; Reference ID : 403147798] |  |  | BILL/01848/2023-2024 | BP/23-24/301 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0 | 0
14 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N | SM/13987 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DHUMPARA PWSS , Zone-I (TW No. I, II) and Zone-II (TW No- I, II and III) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000425/2023-2024 | 1340/NMD | 08/08/2023 | 07/09/2023 | A.G. ENTERPRISE | 60.95 | 17.96 | 29.46 | 50
Total | [13 empty] | 681.82 | 97.38 | 14.28