## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Construction of Different components of Upper Tandu Forest (M) i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Nagrakata under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2022-2023 | 676/JD | 16/03/2023 | 12/09/2023 | NISHITH RANJAN KARMAKAR | 96 | 52.03 | 54.2 | 100
2 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 160/JD | 28/04/2023 |  | Resource Division | 2.08 | 0 | 0 | 0
3 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 2057/JD | 09/01/2024 |  | Resource Division | 2.22 | 0 | 0 | 0
4 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | New Service Connection Charge for UPPER TENDU FOREST NEW KHUNIA MAHABARI, under MATELLI CCC [APPLICATION NO. 4003177258 ; Reference ID : 403033825] |  |  | BILL/01009/2023-2024 | BP/23-24/97 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Infrastructure Cost for UPPER TENDU FOREST NEW KHUNIA MAHABARI, under MATELLI CCC [APPLICATION NO. 100000082756 ; Reference ID : 860274516] |  |  | BILL/01010/2023-2024 | BP/23-24/97 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.11 | 0 | 0 | 0
6 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UPPER TENDU FOREST PWSS, TW No I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000881/2022-2023 | 364/NMD | 29/03/2023 | 28/04/2023 | SAIKAT SINHA | 12.05 | 6.02 | 49.94 | 100
Total | [13 empty] | 116.14 | 58.04 | 49.98