## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 |  | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Construction of Boundary wall, Foot Path, Drain, pipeline for washout at HW site of Binnaguri PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000085/2024-2025 | 1175/JD | 23/08/2024 | 22/10/2024 | BISWANATH GHOSH | 27.55 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site of Binnaguri PWSS in connection with Jal Jeevan Mission at Block ¿ Sadar Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000099/2024-2025 | 800/RWS | 20/08/2024 | 19/09/2024 | PRADIP KUMAR SHIL | 7.67 | 0 | 0 | 0
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Construction of different components of Binnaguri PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2022-2023 | 751/JD | 24/03/2023 | 20/09/2023 | BISWANATH GHOSH | 226.15 | 72.04 | 31.85 | 78
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 154/JD | 28/04/2023 |  | Resource Division | 17.1 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 2003/JD | 08/01/2024 |  | Resource Division | 6.23 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Infrastructure Cost for BINNAGURI T/W-I, under HALDIBARI CCC , [APPLICATION NO. 4003341115, Reference ID : 403164679] |  |  | BILL/02031/2023-2024 | BP/23-24/313 | 28/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.66 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Infrastructure Cost for BINNAGURI T/W-II, under HALDIBARI CCC , [APPLICATION NO. 4003341205, Reference ID : 403165171] |  |  | BILL/02032/2023-2024 | BP/23-24/313 | 28/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.38 | 0 | 0 | 0
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BINNAGURI(JALPAIGURI SADAR BLOCK) PWSS, TW no I & II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000349/2023-2024 | 1310/NMD | 04/08/2023 | 03/09/2023 | UTTAM PAUL | 22.21 | 0 | 0 | 0
Total | [13 empty] | 361.37 | 72.04 | 19.93