## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Dhupguri, Rajganj and Balance of Banarhat Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2024-2025 | 940/JD | 07/08/2024 | 06/10/2024 | AKG UDYOG | 25.37 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Construction of different components of Gadang Pratham Khanda PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000475/2022-2023 | 779/JD | 27/03/2023 | 23/09/2023 | M/S. DOLPHIN CONSTRUCTION CO. | 222.91 | 66.53 | 29.84 | 20
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 152/JD | 28/04/2023 |  | Resource Division | 26.83 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 1838/JD | 15/12/2023 |  | Resource Division | 2.62 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | New Service Connection Charge for GADANG PRATHAM KHANDA PWSS , T/W-I under DHUPGURI CCC, APPLICATION NO. 4003412908 Reference ID : 403221510 |  |  | BILL/00388/2024-2025 | BP/24-25/73 | 30/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.3 | 0 | 0 | null
6 | JALPAIGURI | Dhupguri | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | New Service Connection Charge for GADANG PRATHAM KHANDA PWSS, TW no II, under DHUPGURI CCC APPLICATION NO. 4003290916 Consumer ID : 403123851 |  |  | BILL/00536/2024-2025 | BP/24-25/130 | 24/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | null
7 | JALPAIGURI | Dhupguri | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/14665 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GADANG PRATHAM KHANDA PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000657/2023-2024 | 1471/NMD | 17/08/2023 | 16/09/2023 | S.P. ENTERPRISE (KOLKATA) | 20.63 | 0 | 0 | 0
Total | [13 empty] | 312.07 | 66.53 | 21.32