## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Construction of different components of Gendrapara Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Banerhat under Jalpaiguri Division | Assistant Engineer,HQ | Junior Engineer | ORD/000447/2022-2023 | 717/JD | 20/03/2023 | 16/09/2023 | ANUGRAH CONSTRUCTION PVT. LTD. | 424.78 | 203.97 | 48.02 | 60
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1093/JD | 24/08/2023 |  | Resource Division | 27.95 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 1829/JD | 15/12/2023 |  | Resource Division | 14.72 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W I under BANARHAT CCC [APPLICATION NO. 4003193569 ; Reference ID : 403045945] |  |  | BILL/01001/2023-2024 | BP/23-24/98 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W I under BANARHAT CCC [APPLICATION NO. 100000083816 ; Reference ID : 860275316] |  |  | BILL/01002/2023-2024 | BP/23-24/98 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W II under BANARHAT CCC [APPLICATION NO. 4003193576 ; Reference ID : 403045947] |  |  | BILL/01003/2023-2024 | BP/23-24/98 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W II under BANARHAT CCC [APPLICATION NO. 100000083810 ; Reference ID : 860275310] |  |  | BILL/01004/2023-2024 | BP/23-24/98 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W III under BANARHAT CCC [APPLICATION NO. 4003193581 ; Reference ID : 403045948] |  |  | BILL/01005/2023-2024 | BP/23-24/98 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W III under BANARHAT CCC [APPLICATION NO. 100000083811 ; Reference ID : 860275311] |  |  | BILL/01006/2023-2024 | BP/23-24/98 | 12/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.38 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GENDRAPARA TG (D) PWSS, TW NO I, II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000240/2023-2024 | 1254/NMD | 31/07/2023 | 30/08/2023 | SUNRISE ENGINEERING CORPORATION | 36.78 | 12.16 | 33.05 | 80
Total | [13 empty] | 545.02 | 216.13 | 39.66