## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 |  | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | Balance Work of Distribution System for Patkata Zone- III Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000055/2024-2025 | 957/JD | 09/08/2024 | 07/12/2024 | JAYA SARKAR | 49.34 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | Construction of different components of Patkata Zone-III PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc In connection with Jal Jeevan Mission at Block- Jalpaiguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000069/2023-2024 | 398/A/JD | 06/06/2023 | 03/12/2023 | GARGO TRADERS | 434.09 | 153.32 | 35.32 | 70
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 1369/JD | 27/09/2023 |  | Resource Division | 23.28 | 0 | 0 | 0
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 1883/JD | 20/12/2023 |  | Resource Division | 15.62 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | New Service Connection Charge for new service connection at PATKATA, T/W-II, ZONE-III, UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003426181 Reference ID : 403231210 |  |  | BILL/00482/2024-2025 | BP/24-25/101 | 25/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | null
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | New Service Connection Charge for PATKATA, ZONE-III, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341668, Reference ID : 403171646] |  |  | BILL/02141/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.89 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2023-2024 | 1217/NMD | 26/07/2023 | 25/08/2023 | MALAY KUMAR SAHA | 24.37 | 8.85 | 36.33 | 70
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-III)of PATKATA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  | Junior Engineer | ORD/001705/2023-2024 | 438/SMSD | 28/03/2024 | 04/04/2024 | SAIKAT SINHA | 0.73 | 0 | 0 | 0
Total | [13 empty] | 599.68 | 162.17 | 27.04