## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 |  | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 22/08/2024 | GURUKUL INFOTECH | 4.83 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Construction of different components of Kantadighi Kumarpara T.G. PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000063/2023-2024 | 247/JD | 10/05/2023 | 06/11/2023 | S.S. CONSTRUCTION | 465.21 | 170.41 | 36.63 | 20
4 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 1092/JD | 24/08/2023 |  | Resource Division | 60.02 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 2012/JD | 09/01/2024 |  | Resource Division | 15.28 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. I, under MAL CCC [APPLICATION NO. 4003303019 , Reference ID : 403132354] |  |  | BILL/01791/2023-2024 | BP/23-24/261 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. I, under MAL CCC [APPLICATION NO. 100000096843 , Reference ID : 860287693] |  |  | BILL/01792/2023-2024 | BP/23-24/260 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.14 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. II, under MAL CCC [APPLICATION NO. 4003303022 , Reference ID : 403132353] |  |  | BILL/01793/2023-2024 | BP/23-24/262 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. II, under MAL CCC [APPLICATION NO. 100000096844 , Reference ID : 860287694] |  |  | BILL/01794/2023-2024 | BP/23-24/263 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. III, under MAL CCC [APPLICATION NO. 4003303010 , Reference ID : 403132351] |  |  | BILL/01795/2023-2024 | BP/23-24/264 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. III, under MAL CCC [APPLICATION NO. 100000096846 , Reference ID : 860287696] |  |  | BILL/01796/2023-2024 | BP/23-24/265 | 19/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.25 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN KANTADIGHI KUMARPARA TEA GARDEN PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000996/2023-2024 | 1994/NMD | 21/12/2023 | 20/01/2024 | SUBODH KUMAR BANIK | 25.51 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KANTADIGHI KUMAPARA TG PWSS at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001571/2023-2024 | 655/NMD | 15/03/2024 | 14/04/2024 | BONANZA ENTERPRISE | 12.34 | 5.86 | 47.54 | 80
Total | [13 empty] | 629.14 | 176.27 | 28.02