## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 |  | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 22/08/2024 | GURUKUL INFOTECH | 4.43 | 0 | 0 | 0
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | Construction of different components of Uttar Mouamari PWSS i.e TW, Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc,i.c.w.Jal Jeevan Mission at Block-Maynaguri under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000072/2023-2024 | 699/JD | 13/07/2023 | 09/01/2024 | M/S SIBU DEY AND CO. | 250.23 | 69.38 | 27.73 | 60
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | Construction of boundary wall with gate,drain,Land development and pathway and laying pipe line at 2 nd site of uttar Mouamari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000080/2024-2025 | 801/RWS | 20/08/2024 | 19/09/2024 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 8.47 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | Construction of Boundary Wall with gate, drain, Land Development and pathway and Laying Pipe line at H/W site of Uttar Mouamari Piped Water Supply Scheme under Jalpaiguri Division PHE, DTE. | Assistant Engineer | Junior Engineer | ORD/000088/2024-2025 | 1298/JD | 05/09/2024 | 04/11/2024 | M/S SIBU DEY AND CO. | 24 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1084/JD | 24/08/2023 |  | Resource Division | 47.75 | 0 | 0 | 0
7 | JALPAIGURI | Maynaguri | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 2059/JD | 10/01/2024 |  | Resource Division | 7.17 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | New Service Connection Charge for UTTAR MAUAMARI, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376055 Reference ID : 403191647 |  |  | BILL/00150/2024-2025 | BP/24-25/25 | 09/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.2 | 0 | 0 | null
9 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | New Service Connection Charge for UTTAR MOUAMARI, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003401393 Reference ID : 403212002 |  |  | BILL/00286/2024-2025 | BP/24-25/43 | 28/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.05 | 0 | 0 | null
10 | JALPAIGURI | Maynaguri | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR MAUAMARI PWSS, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000457/2023-2024 | 1433/NMD | 10/08/2023 | 09/09/2023 | RAJEEV RANJAN OJHA | 20.68 | 0 | 0 | 0
Total | [13 empty] | 425.42 | 69.38 | 16.31