## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Retrofitting works related to FHTC at Barokamat, Dhaurapara for Argi Garalbari W/S Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000040/2023-2024 | 392/RWS | 25/04/2023 | 09/05/2023 | BISWAJIT BHADURI | 3.54 | 3.53 | 99.74 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Construction of different components for Rejuvenation of Arji Garalbari PWSS i.e. TW, Pump Houses, IEP, Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri sadar under Jalpaiguri Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/000109/2023-2024 | 434/JD. | 08/06/2023 | 23/07/2023 | ASIM GUPTA | 40.15 | 4.72 | 11.76 | 40
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site for Rejuvenation of Araji Garalbari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000255/2023-2024 | 941/JD | 08/08/2023 | 22/09/2023 | LOKNATH CONSTRUCTION | 17.31 | 8.62 | 49.8 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Construction of Pump House (3.60M X 2.40M) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Arji Garalbari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 169/JD | 19/01/2023 | 18/02/2023 | ABHIJIT SARKAR | 10.88 | 5.41 | 49.71 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Providing Functional Household Tap connection (FHTC) at Paharer Hat in connection with JJM at Arji Garalbari Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P.H.E. Dte.(Part-I) | Assistant Engineer | Junior Engineer | ORD/000420/2022-2023 | 600/JD | 09/03/2023 | 30/03/2023 | RANJIT KARMAKAR | 4.85 | 2.41 | 49.73 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Rising Main Connections(at 3rd TW site) including other necessary arrangement for Rejuvenation of Araji Garalbari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000490/2022-2023 | 289/RWS | 29/03/2023 | 12/04/2023 | ALICK DATTA | 1.81 | 0.9 | 49.5 | 100
7 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | New Service Connection Charge for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 4003103534 ; Reference ID : 402988696] |  |  | BILL/00006/2023-2024 | BP/23-24/33 | 09/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Infrastructure Cost for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 100000075210 ; Reference ID : 860266620] |  |  | BILL/00007/2023-2024 | BP/23-24/47 | 04/07/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.97 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Infrastructure Cost for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 100000075210 ; Reference ID : 860266620] |  |  | BILL/00493/2023-2024 | null | 23/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.97 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | New Service Connection Charge for ARGI GARALBARI, T/W III, under PANDAPARA CCC [APPLICATION NO. 4003099007 ; Reference ID : 402983422] |  |  | BILL/00520/2023-2024 | BP/23-24/115 | 06/10/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Infrastructure Cost for ARGI GARALBARI, T/W III, under PANDAPARA CCC [APPLICATION NO. 100000074333 ; Reference ID : 860264763] |  |  | BILL/00521/2023-2024 | BP/23-24/115 | 06/10/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.03 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ARJI GARALBARI Piped Water Supply Scheme, TW No.- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2023-2024 | 812/NMD | 20/07/2023 | 19/08/2023 | M/S ANJALI ENTERPRISE | 11.53 | 5.48 | 47.54 | 90
13 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS | SM/15030 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ARJI GARALBARI PWSS,at TW NO IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000134/2023-2024 | 813/NMD | 20/07/2023 | 19/08/2023 | SARKAR ELECTRIC | 11.71 | 5.86 | 50 | 100
Total | [13 empty] | 121.21 | 36.93 | 30.46