## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Bhangarhat PWSS , in connection with Rejuvenation of Bhangarhat PWSS under Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000098/2023-2024 | 349/JD | 24/05/2023 | 23/07/2023 | DIPAK KUMAR CHAKRABORTY | 36.26 | 4.87 | 13.42 | 40
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Laying distribution system for balanced DI pipeline from Ranirhat More towards Dhupguri for Bhangarhat PWSS at Maynaguri Block under Jalapaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000734/2023-2024 | 2454/JD | 23/02/2024 | 08/03/2024 | DIPAK KUMAR CHAKRABORTY | 11.62 | 5.95 | 51.2 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 1053/JD | 24/08/2023 |  | Resource Division | 2.59 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | New Service Connection Charge for REJUVENATION OF BHANGARHAT, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376107 Reference ID : 403191657 |  |  | BILL/00153/2024-2025 | BP/24-25/25 | 09/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.2 | 0 | 0 | null
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Bhangarhat Piped Water Supply Scheme | SM/15032 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANGARHAT PWSS, TW NO- I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000183/2023-2024 | 1220/NMD | 26/07/2023 | 25/08/2023 | GURUKRIPA ENTERPRISE | 11.5 | 0 | 0 | 0
Total | [13 empty] | 70.17 | 10.81 | 15.41