## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/15033 | Augmentation | Construction of different components of Rejuvenation Chauhaddi PWSS i.e. TW, Pump Houses, Water distribution Network, , RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000100/2023-2024 | 350/JD | 24/05/2023 | 23/07/2023 | HARIPADA BANERJEE | 61.11 | 22.32 | 36.53 | 60
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/15033 | Augmentation | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. |  |  | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 06/12/2023 | SAHA CONSTRUCTION | 37.11 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme | SM/15033 | Augmentation | New Service Connection Charge for REJUVENATION OF CHAUHADDI PWSS, TW NO IV, under DHUPGURI CCC APPLICATION NO. 4003460809 Reference ID : 403255219 |  |  | BILL/00970/2024-2025 | BP/24-25/166 | 14/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.39 | 0 | 0 | null
Total | [13 empty] | 103.61 | 22.32 | 21.55