## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | Construction of different components of Rejuvenation of Raipur T.G. PWSS i.e TW, pump houses,water distribution network, Boundary wall, Rising main, etc in connection with JJM at Block - Jalpaiguri Sadar under jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2023-2024 | 385/JD | 01/06/2023 | 31/07/2023 | NEW KUNDU ENTERPRISE | 49.45 | 18.26 | 36.92 | 50
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | Land devlopment at 2nd site under Raipur T.G. Piped Water Supply Scheme under Jalpiaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000494/2022-2023 | 286/RWS | 29/03/2023 | 08/04/2023 | NEW KUNDU ENTERPRISE | 0.98 | 0.98 | 99.88 | 100
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | New Service Connection Charge for RAIPUR TEA GARDEN,T/W-III, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003343597 Reference ID : 403174733 |  |  | BILL/00161/2024-2025 | BP/24-25/14 | 23/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.87 | 0 | 0 | null
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS | SM/15071 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF RAIPUR TEA GARDEN PWSS,at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 1544/NMD | 01/09/2023 | 01/10/2023 | SAIKAT SINHA | 12.42 | 4.31 | 34.72 | 60
Total | [13 empty] | 70.73 | 23.55 | 33.3