## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Emergency restoration work of pucca road that was damaged during pipe laying at Uttar Dangapara & Dakshin Sakoajhora Piped Water Supply Scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000022/2023-2024 | 122/JD | 28/04/2023 | 12/05/2023 | PARESH CHANDRA GUHA | 3.91 | 3.9 | 99.59 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Uttar Dangapara & Dakshin Sakoajhora PWSS , in connection with Rejuvenation of Uttar Dangapara & Dakshin Sakoajhora PWSS under Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000093/2023-2024 | 2000/JD | 19/05/2023 | 18/07/2023 | NARESH SEN | 19.29 | 4.54 | 23.54 | 15
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Uttar Dangapara & Dakshin Sakoajhora PWSS , in connection with Rejuvenation of Uttar Dangapara & Dakshin Sakoajhora PWSS under Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000095/2023-2024 | 333/JD | 22/05/2023 | 21/07/2023 | NARESH SEN | 19.29 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 1056/JD | 24/08/2023 |  | Resource Division | 2.4 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | New Service Connection Charge for new service connection at REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III GAIRKATA CCC APPLICATION NO. 4003441947 Reference ID : 403241902 |  |  | BILL/00589/2024-2025 | BP/24-25/143 | 01/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | null
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Infrastructure development cost for new service connection at REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III GAIRKATA CCC APPLICATION NO. 100000111357 Reference ID : 860303377 |  |  | BILL/00590/2024-2025 | BP/24-25/143 | 01/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.74 | 0 | 0 | null
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/15078 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000170/2023-2024 | 1212/NMD | 26/07/2023 | 25/08/2023 | TAPAN BISWAS | 11.07 | 2.91 | 26.24 | 50
Total | [13 empty] | 60.52 | 11.34 | 18.75