## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Construction of different components of Rejuvenation of Manabari Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 937/JD | 08/08/2023 | 06/11/2023 | TARAKESWAR PRASAD | 97.86 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Construction of Approach Culvert with Guard Wall at H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000381/2022-2023 | 359/JD | 20/02/2023 | 13/03/2023 | M/S A.B.G. CONSTRUCTION | 2.93 | 2.92 | 99.66 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Construction of G. I. line & concrete block & piller for culvert for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000483/2022-2023 | 802/JD | 29/03/2023 | 19/04/2023 | M/S A.B.G. CONSTRUCTION | 3.02 | 2.98 | 98.76 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Rejuvenation of Manabari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000593/2023-2024 | 2332/JD | 08/02/2024 | 23/02/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 7.01 | 42.13 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1064/JD | 24/08/2023 |  | Resource Division | 19.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation for Manabari Tea Garden | SM/15082 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MANABARI TEA GARDEN PWSS, AT TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000426/2023-2024 | 1341/NMD | 08/08/2023 | 07/09/2023 | S.P. ENTERPRISE | 20.63 | 0 | 0 | 0
Total | [13 empty] | 160.76 | 12.91 | 8.03