## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Laying distribution system along with ancillary works for Rejuvenation of Bhandani Piped water supply scheme in connection with Jal Jeevan mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ |  | ORD/000009/2024-2025 | 422/JD | 12/06/2024 | 12/07/2024 | SANJIT SAHA | 29.06 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Bhandani PWSS , in connection with Rejuvenation of Bhandani PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000143/2023-2024 | 703/JD | 13/07/2023 | 11/09/2023 | GOURAB GUHA ROY | 36.18 | 11.45 | 31.66 | 15
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 1054/JD | 24/08/2023 |  | Resource Division | 1.25 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME | SM/15094 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANDANI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000062/2023-2024 | 594/NMD | 18/05/2023 | 17/06/2023 | M/S ROYAL ENTERPRISE | 11.45 | 0 | 0 | 0
Total | [13 empty] | 77.94 | 11.45 | 14.7