## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME | SM/15096 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc for Rejuvenation of Bhangamali Piped Water Supply Scheme at Dhupguri Block in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000103/2023-2024 | 389/A/JD | 01/06/2023 | 31/07/2023 | VIBEKANANDA DEY | 35.66 | 4.06 | 11.37 | 37
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME | SM/15096 | Augmentation | Retrofitting works in connection with FHTC works for the habitation of Dangar Bari , Fokkorer Bari , near Chandrakanta School & Providing balanced Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Bhangamali Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. |  |  | ORD/000167/2022-2023 | 1418/JD | 14/07/2022 | 29/07/2022 | MRINMOY KANTI DUTTA | 4.62 | 2.11 | 45.63 | 1
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME | SM/15096 | Augmentation | New Service Connection Charge for BHANGAMALI (REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003401391 Reference ID : 403212005 |  |  | BILL/00285/2024-2025 | BP/24-25/36 | 14/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0 | null
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME | SM/15096 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANGAMALI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000460/2023-2024 | 1436/NMD | 10/08/2023 | 09/09/2023 | SAIKAT SINHA | 11.5 | 3.91 | 34 | 40
Total | [13 empty] | 55.46 | 10.08 | 18.17