## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | SM/15116 | Augmentation | Construction of different components of Rejuvenation of Nakhati Tea Garden PWSS i.e TW, Pump Houses, Boundary Wall, Water Distribution Network (Conversion ), Rising main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000086/2023-2024 | 358/JD. | 25/05/2023 | 24/07/2023 | D. S. ENTERPRISE | 66.52 | 26.26 | 39.48 | 40
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | SM/15116 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1087/JD | 24/08/2023 |  | Resource Division | 9.2 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | SM/15116 | Augmentation | "New Service Connection Charge for (REJU)NAKHATI TG TW NO-III , MAL CCC " APPLICATION NO. 4003377472 Reference ID : 403192833 |  |  | BILL/00171/2024-2025 | BP/24-25/14 | 23/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | null
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | SM/15116 | Augmentation | INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT (REJU)NAKHATI TG TW NO-III , MAL CCC " APPLICATION NO. 100000104920 Reference ID : 860296940 |  |  | BILL/00172/2024-2025 | BP/24-25/14 | 23/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.8 | 0 | 0 | null
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | SM/15116 | Augmentation | "New Service Connection Charge for (REJU)NAKHATI TG TW NO-IV, MAL CCC " APPLICATION NO. 4003377480 Reference ID : 403192836 |  |  | BILL/00173/2024-2025 | BP/24-25/14 | 23/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | null
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | SM/15116 | Augmentation | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT(REJU)NAKHATI TG TW NO-IV, MAL CCC " APPLICATION NO.100000104806 Reference ID : 860297126 |  |  | BILL/00174/2024-2025 | BP/24-25/14 | 23/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.52 | 0 | 0 | null
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme | SM/15116 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAKHATI TEA GARDEN AREA PWSS, TW NO III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000669/2023-2024 | 1484/NMD | 17/08/2023 | 16/09/2023 | PRATIK ROY | 24.25 | 10.17 | 41.93 | 60
Total | [13 empty] | 126.65 | 36.43 | 28.76