## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | Construction of different components of Rejuvenation Of Grassmore Tea Garden PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000126/2023-2024 | 413/A/JD | 07/06/2023 | 06/08/2023 | JAYDEB SAHA | 30.89 | 23.73 | 76.85 | 90
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | Direct boosting arrangement from 2 nd Pump to the Nandu more to Ghasmari Road area due to low tail end pressure along with leftout distribution system and FHTC at Grassmore T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000135/2023-2024 | 794/JD | 24/07/2023 | 01/04/2025 | SUNIL ROY | 11.3 | 0 | 0 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | Construction of Hume Pipe Culvert along with approach way development at 2 nd Pump House Site of Grassmore T.G. Piped water supply Scheme under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000164/2022-2023 | 1434/JD | 18/07/2022 | 02/08/2022 | DEEP CONSTRUCTION | 1.18 | 1.17 | 99.13 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | Remaining part of Laying Distribution System (PART-C ) for Grassmore T.G. AREA P.W.S.S. under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000181/2020-2021 | 1266/JD | 18/11/2020 | 17/01/2021 | ASHIT KUMAR SINGHA | 61.96 | 0 | 0 | 1
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | New Service Connection Charge for GRASSMORE TG, T/W No. III, under NAGRAKATA CCC [APPLICATION NO. 4003285470 ; Reference ID : 403120243] |  |  | BILL/01727/2023-2024 | BP/23-24/240 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | Infrastructure Cost for GRASSMORE TG, T/W No. III, under NAGRAKATA CCC [APPLICATION NO. 100000096116 ; Reference ID : 860288226] |  |  | BILL/01728/2023-2024 | BP/23-24/241 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.21 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GRASSMORE TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000429/2023-2024 | 1346/NMD | 08/08/2023 | 07/09/2023 | BONANZA ENTERPRISE | 11.36 | 11.33 | 99.78 | 100
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme | SM/15130 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
Total | [13 empty] | 703.92 | 36.23 | 5.15