## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Construction of different components of Kholachand Fapri PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. under Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000064/2023-2024 | 266/JD | 10/05/2023 | 06/11/2023 | M/S SARKAR ENTERPRISE | 262.01 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Dhupguri, Rajganj and Balance of Banarhat Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2024-2025 | 940/JD | 07/08/2024 | 06/10/2024 | AKG UDYOG | 25.37 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 53/JD | 09/04/2024 |  | Resource Division | 13.2 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 2049/JD | 09/01/2024 |  | Resource Division | 7.47 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | New Service Connection Charge for KHOLA CHAND FAPRI, TW NO-II, Powe House CCC APPLICATION NO. 4003352425 Reference ID : 403172863 |  |  | BILL/00435/2024-2025 | BP/24-25/87 | 18/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.71 | 0 | 0 | null
6 | JALPAIGURI | Rajganj | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | New Service Connection Charge for KHOLA CHAND FAPRI, TW NO-I, POWER HOUSE CCC APPLICATION NO. 4003352414 Consumer ID : 403172861 |  |  | BILL/00524/2024-2025 | BP/24-25/123 | 16/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.99 | 0 | 0 | null
7 | JALPAIGURI | Rajganj | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME | SM/15263 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHOLACHAND FAPRI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 1276/NMD | 02/08/2023 | 01/09/2023 | P.K.ENGINEERING | 22.11 | 0 | 0 | 0
Total | [13 empty] | 354.86 | 0 | 0