## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Construction of different components of Chalsa Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Matiali under Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 24/JD | 10/04/2023 | 07/10/2023 | PRASENJIT BASAK | 195.5 | 110.48 | 56.51 | 65
2 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Sinking of 2 Nos Deep Rig Bored Tube Well by ODEX-195 method of drilling with 2 Nos Pump House(3.6m X 2.4m) and Boundary Wall including Pump House to distribution Line Connection for Rejuvenation of Chalsa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000275/2023-2024 | 614/JD | 30/06/2023 | 30/07/2023 | S. N. POLYMERS PVT. LTD. | 40.47 | 13.79 | 34.07 | 35
4 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Retrofitting and Repairing work related to Laying Distribution System in Mangal Bar market area at Chalsa Rejuvenation Water Supply Scheme under Jalpaiguri Division, PHE DTE. |  | Junior Engineer | ORD/000829/2021-2022 | 1072/W/JSSD | 25/01/2022 | 14/02/2022 | DEEP CONSTRUCTION | 4.14 | 4.09 | 98.72 | 0
5 | JALPAIGURI | Matiali | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 2034/JD | 09/01/2024 |  | Resource Division | 6.65 | 0 | 0 | 0
6 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | New Service Connection Charge for CHALSA TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 4003197396, Reference ID : 403049082] |  |  | BILL/00607/2023-2024 | BP/23-24/85 | 18/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Infrastructure Cost for CHALSA TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 100000084427, Reference ID : 860276303] |  |  | BILL/00608/2023-2024 | BP/23-24/85 | 18/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.14 | 0 | 0 | 0
8 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | New Service Connection Charge for CHALSA TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 4003197399, Reference ID : 403049084] |  |  | BILL/00609/2023-2024 | BP/23-24/85 | 18/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
9 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Infrastructure Cost for CHALSA TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 100000084429, Reference ID : 860276310] |  |  | BILL/00610/2023-2024 | BP/23-24/85 | 18/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
10 | JALPAIGURI | Matiali | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHALSA TEA GARDEN (ZONE-I,II) PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000314/2023-2024 | 1278/NMD | 02/08/2023 | 01/09/2023 | MASSK ENGINEERING WORKS | 24.55 | 0 | 0 | 80
Total | [13 empty] | 314.46 | 128.36 | 40.82