## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME | SM/15338 | Augmentation | Construction of different components of Augmentation of Angrabhasa PWSS i.e. TW, Pump Houses, Boundary Walls. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 1436/JD | 05/10/2023 | 04/12/2023 | M/S ROY & SARKAR CONSTRUCTION | 27.72 | 5.71 | 20.6 | 35
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME | SM/15338 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Nagrakata block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000453/2023-2024 | 1287/RWS | 28/11/2023 | 28/12/2023 | B.M CONSTRUCTION | 3.11 | 1.56 | 50 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME | SM/15338 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1071/JD | 24/08/2023 |  | Resource Division | 41.27 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME | SM/15338 | Augmentation | New service connection charge for (reju) Angrabhasa PWSS tw-IV Application No-4003418417 Reference Id-403225912 |  |  | BILL/00366/2024-2025 | BP/24-25/81 | 07/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9 | 0 | 0 | null
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME | SM/15338 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ANGRABHASA PWSS at TW NO IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/001616/2023-2024 | 656/NMD | 15/03/2024 | 14/04/2024 | SAIKAT SINHA | 12.6 | 4.25 | 33.74 | 60
Total | [13 empty] | 93.7 | 11.52 | 12.29