## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 |  | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | Distribution System and Functional Household Tap Connection (FHTC) for Patkata Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000028/2024-2025 | 740/JD | 26/07/2024 | 09/10/2024 | M/S SIBU DEY AND CO. | 118.85 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | Construction of different components of Patkata Zone- I Piped Water Supply Scheme i.e TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2023-2024 | 1706/JD | 04/12/2023 | 01/06/2024 | GARGO TRADERS | 546.65 | 87.24 | 15.96 | 60
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 1371/JD | 27/09/2023 |  | Resource Division | 48.31 | 0 | 0 | 0
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 2076/JD | 10/01/2024 |  | Resource Division | 26.02 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | New Service Connection Charge for PATKATA, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341718, Reference ID : 403171608] |  |  | BILL/02142/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.15 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | New Service Connection Charge for PATKATA, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 40033417720, Reference ID : 403172408] |  |  | BILL/02143/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.09 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2023-2024 | 1279/NMD | 02/08/2023 | 01/09/2023 | M/S BHOWMICK & CO. | 35.98 | 0 | 0 | 0
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME | SM/15339 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-I)of PATKATA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  | Junior Engineer | ORD/001703/2023-2024 | 436/SMSD | 28/03/2024 | 04/04/2024 | M/S ANJALI ENTERPRISE | 0.73 | 0 | 0 | 0
Total | [13 empty] | 832.2 | 87.24 | 10.48