## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Construction of different components of Sonakhuli PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000013/2023-2024 | 39/JD | 13/04/2023 | 10/10/2023 | JAYANTA GHOSH | 196.47 | 0 | 0 | 11
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Dhupguri, Rajganj and Balance of Banarhat Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2024-2025 | 940/JD | 07/08/2024 | 06/10/2024 | AKG UDYOG | 25.37 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 157/JD | 28/04/2023 |  | Resource Division | 12.08 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 1840/JD | 15/12/2023 |  | Resource Division | 4.51 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | New Service Connection Charge for new service connection at SONAKHULI,T/W-I, GAIRKATA CCC APPLICATION NO. 4003424435 Reference ID : 403230061 |  |  | BILL/00485/2024-2025 | BP/24-25/101 | 25/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | null
6 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Infrastructure development cost for new service connection at SONAKHULI,T/W-I, GAIRKATA CCC APPLICATION NO. 100000110438 Reference ID : 860302768 |  |  | BILL/00486/2024-2025 | BP/24-25/101 | 25/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.53 | 0 | 0 | null
7 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | New Service Connection Charge for new service connection at SONAKHULI,T/W-II, GAIRKATA CCC APPLICATION NO. 4003424430 Reference ID : 403230062 |  |  | BILL/00487/2024-2025 | BP/24-25/101 | 25/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | null
8 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Infrastructure development cost for new service connection at SONAKHULI,T/W-II, GAIRKATA CCC APPLICATION NO. 100000110437 Reference ID : 860302767 |  |  | BILL/00488/2024-2025 | BP/24-25/101 | 25/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.17 | 0 | 0 | null
9 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SONAKHULI PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000239/2023-2024 | 1253/NMD | 31/07/2023 | 30/08/2023 | GOENKA ENTERPRISE | 20.65 | 7.12 | 34.48 | 60
Total | [13 empty] | 271.41 | 7.12 | 2.62