## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | KHUKLUNG PIPED WATER SUPPLY SCHEME | SM/15953 | New | Construction of different components of Khuklung Mini PWSS ie. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Dhupguri Block, under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000274/2023-2024 | 1265/JD | 13/09/2023 | 12/12/2023 | DEBASISH DEY | 63.25 | 0 | 0 | 90
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | KHUKLUNG PIPED WATER SUPPLY SCHEME | SM/15953 | New | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 2001/JD | 08/01/2024 | 08/01/2024 | Resource Division | 0.73 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | KHUKLUNG PIPED WATER SUPPLY SCHEME | SM/15953 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHUKHLUNG PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000680/2023-2024 | 1492/NMD | 17/08/2023 | 16/09/2023 | SANJIB SAHA | 6.09 | 0 | 0 | 0
Total | [13 empty] | 70.06 | 0 | 0