## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Construction of differet components of Baragharia Zone-II PWSS i.e TW, Pump Houses, Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. in connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000053/2023-2024 | 357/JD. | 25/05/2023 | 21/11/2023 | M.S ENTERPRISE | 166.28 | 45.01 | 27.07 | 65
2 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Construction of differet components of Baragharia Zone-I PWSS i.e TW, Pump Houses , Water distribution Network, OHR, Boundary Wall , RISING MAIN , FHTC etc. in connection with Jal Jeevan Mission at Block Kranti under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 356/JD | 25/05/2023 | 21/11/2023 | M.S ENTERPRISE | 246.82 | 69.83 | 28.29 | 40
3 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 1078/JD | 24/08/2023 |  | Resource Division | 38.3 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 2074/JD | 10/01/2024 |  | Resource Division | 8.03 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA,TW NO-I, KRANTI CCC APPLICATION NO. 100000109544 Reference ID : 860302004 |  |  | BILL/00405/2024-2025 | BP/24-25/81 | 07/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.98 | 0 | 0 | null
7 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA,TW NO-II, KRANTI CCC APPLICATION NO. 100000109538 Reference ID : 860301298 |  |  | BILL/00406/2024-2025 | BP/24-25/81 | 07/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.51 | 0 | 0 | null
8 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | New Service Connection Charge for BARA GHARIA,TW NO-II, KRANTI CCC APPLICATION NO. 4003426943 Reference ID : 403231623 |  |  | BILL/00407/2024-2025 | BP/24-25/81 | 07/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | null
9 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | New Service Connection Charge for BARA GHARIA,TW NO-I, KRANTI CCC APPLICATION NO. 4003426904 Reference ID : 403231622 |  |  | BILL/00408/2024-2025 | BP/24-25/81 | 07/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | null
10 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PWSS at TW NO I,II, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001570/2023-2024 | 654/NMD | 15/03/2024 | 14/04/2024 | SUBHRANGSHU GUHARAJA | 23.9 | 9 | 37.65 | 50
Total | [13 empty] | 524.83 | 123.83 | 23.59