## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | Construction of different components of Patharjhora Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2023-2024 | 346/JD. | 23/05/2023 | 19/11/2023 | SRINIWAS AGARWAL | 208.93 | 64.48 | 30.86 | 45
2 | JALPAIGURI | Mal | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | Sinking of one no. Tube Well by Modified DTH - ODEX big dia tube well 200x150 mm dia for Pathorjhora piped water supply scheme i.c.w. Jal jeevan Mission at Mal Block under Jalpaiguri Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000300/2023-2024 | 1357/JD | 26/09/2023 | 26/10/2023 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.54 | 7.74 | 46.78 | 100
4 | JALPAIGURI | Mal | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | Sinking of 2 (Two) Nos Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Patharjohra Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000826/2023-2024 | 2750/JD | 14/03/2024 | 13/04/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.26 | 16.69 | 50.18 | 100
5 | JALPAIGURI | Mal | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 2062/JD | 10/01/2024 |  | Resource Division | 6.09 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | New Service Connection Charge for PATHORJHORA, T/W- I, under ODLABARI CCC, [APPLICATION NO. 4003343265, Reference ID : 403165544] |  |  | BILL/02160/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | New Service Connection Charge for PATHORJHORA, T/W- I, under ODLABARI CCC, [APPLICATION NO. 100000100929, Reference ID : 860293129] |  |  | BILL/02161/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.03 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | New Service Connection Charge for PATHORJHORA, T/W-II, under ODLABARI CCC, [APPLICATION NO. 4003344810, Reference ID : 403166839] |  |  | BILL/02162/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | New Service Connection Charge for PATHORJHORA, T/W-II, under ODLABARI CCC, [APPLICATION NO. 100000101095, Reference ID : 860293135] |  |  | BILL/02163/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.24 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHARJOHRA TEA GARDEN PWSS, ,TW no I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000857/2023-2024 | 1812/NMD | 31/10/2023 | 30/11/2023 | CHOWDHURY AND BASU ENTERPRISE | 29.21 | 0 | 0 | 0
Total | [13 empty] | 338.31 | 88.91 | 26.28