## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 736/JD | 26/07/2024 | 09/10/2024 | MOTI INDUSTRIES | 128.89 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000101/2024-2025 | 874/JD | 31/07/2024 | 27/01/2025 | SOUMEN GHOSH | 0.88 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Construction of different components of Barapatina Nutanbus Zone-II PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000128/2023-2024 | 408/A/JD | 07/06/2023 | 04/12/2023 | UNIBRO INFRASERV PRIVATE LIMITED | 434.44 | 116.28 | 26.77 | 70
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). |  |  | ORD/000295/2023-2024 | 855/JD | 31/07/2023 | 27/01/2024 | SOUMEN GHOSH | 0.88 | 0 | 0 | 20
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000570/2023-2024 | 2197/JD | 25/01/2024 | 23/07/2024 | SOUMEN GHOSH | 0.88 | 0.56 | 63.84 | 0
6 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 1884/JD | 20/12/2023 |  | Resource Division | 14.51 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-II, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341742, Reference ID : 403172228] |  |  | BILL/02146/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.01 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-II, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003351981, Reference ID : 403172665] |  |  | BILL/02147/2023-2024 | BP/23-24/324 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.85 | 0 | 0 | 0
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARAPATINA NUTANBUS PWSS, ZONE-II, TW no I, II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000184/2023-2024 | 1221/NMD | 26/07/2023 | 25/08/2023 | UTTAM PAUL | 21.67 | 0 | 0 | 0
Total | [13 empty] | 615.01 | 116.84 | 19