## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Construction of different components of Kurti Tea Garden (Zone-I, II and III) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2023-2024 | 263/JD | 10/05/2023 | 06/11/2023 | S. N. POLYMERS PVT. LTD. | 308.54 | 0 | 0 | 0
2 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 167/JD | 28/04/2023 |  | Resource Division | 56.03 | 0 | 0 | 0
3 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 2038/JD | 09/01/2024 |  | Resource Division | 6.64 | 0 | 0 | 0
4 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KURTI TEA GARDEN PWSS(TW No- I, II and III), in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000860/2023-2024 | 1804/NMD | 31/10/2023 | 30/11/2023 | SARKAR ELECTRIC | 37.45 | 0 | 0 | 0
Total | [13 empty] | 408.66 | 0 | 0