## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Construction of different components of Paharpur Zone - II PWSS i.e TW, pump houses,water distribution network, OHR, Rising Main, FHTC etc. at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000050/2023-2024 | 130/JD | 28/04/2023 | 25/10/2023 | GARGO TRADERS | 459.33 | 41.98 | 9.14 | 50
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Balance Work of Distribution System for Paharpur Zone - II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000052/2024-2025 | 945/JD | 07/08/2024 | 05/12/2024 | PRIYABRATA KARMAKAR | 24.12 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000122/2023-2024 | 383/A/JD | 01/06/2023 | 28/11/2023 | RUPA PRASAD | 0.88 | 0.19 | 21.53 | 50
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2023 to 31.05.2024)". | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000533/2023-2024 | 1677/JD | 24/11/2023 | 22/05/2024 | RUPA PRASAD | 0.88 | 1.42 | 161.09 | 100
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1077/JD | 24/08/2023 |  | Resource Division | 35.1 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1508/JD | 13/10/2023 |  | Resource Division | 13.79 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 1886/JD | 20/12/2023 |  | Resource Division | 13.79 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | New Service Connection Charge for new service connection at PAHARPUR, T/W-I, ZONE-II, UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003427350 Reference ID : 403231842 |  |  | BILL/00481/2024-2025 | BP/24-25/101 | 25/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.78 | 0 | 0 | null
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PAHARPUR PIPED WATER SUPPLY SCHEME , ZONE-II, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000131/2023-2024 | 811/NMD | 20/07/2023 | 19/08/2023 | M/S RATAN KUMAR DASGUPTA AND CO. | 21.52 | 0 | 0 | 0
Total | [13 empty] | 580.18 | 43.59 | 7.51