## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | Augmentation | Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling, 2 Nos Pump House (2.4m x 3.6m) and 2 Nos Boundary Wall (3rd and 4th Site) along with Laying Distribution System including Rising Main in connection with Jal Jeevan Mission for Rejuvenation of Gatia Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000068/2023-2024 | 292/JD | 15/05/2023 | 13/08/2023 | RANJEET SINGH BENIWAL | 106.29 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1060/JD | 24/08/2023 |  | Resource Division | 3.73 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GATIA TEA GARDEN PWSS, TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000851/2023-2024 | 1803/NMD | 31/10/2023 | 30/11/2023 | SANJIB SAHA | 20.9 | 0 | 0 | 0
Total | [13 empty] | 130.92 | 0 | 0